## Ausfüllhinweise (Guidance note)
Ausfüllhinweise Guidance notes
Logframe
Logframes haben zum Ziel, ein gemeinsames Projektverständnis bei Gebern und Implementierern durch die Konkretisierung von Aktivitäten, Resultaten und Zielsetzungen herzustellen. Die aufgezeigte Interventionslogik beschreibt die dem Projekt zugrundeliegende Strategie basierend auf kausalen Zusammenhängen. | Logframes display the results that the project/programme wishes to achieve and by which means this should be accomplished. Thus allowing both donors and implementing partners to apply clear and logical thought when designing their projects and programmes and to analyse the progress of the actions and their effects throughout the project/programme cycle as well as their success in the end.
Oberziel | Impact
Das übergeordnete (strategische) Ziel zu dem das Projekt/Programme einen Beitrag leisten soll, bzw. die langfristige Verbesserungen für die Zielgruppe. Dies kann nie von einem Projekt/Programm alleine bewältigt werden sondern steht im Zusammenhang mit anderen nationalen und internationalen Bemühungen. | The impact of a programme/project describes the overall long-term goal that should be achieved. This cannot be accomplished by one project/programme alone but rather in a broad action by a number of interventions. It places the project/programme into a international/national framework and strategy.
Projektziel/Programmziel | Outcome
Das Projektziel/Programmziel beschreibt einen konkreten Zustand und adressiert die in der Bedarfsanalyse definierten humanitären Bedarfe der Zielbevölkerung. Es definiert die angestrebten Veränderungen von Verhalten und Lebensumständen der Zielgruppe, d.h. die direkte kurz- oder mittelfristige Wirkung der Resultate der Intervention. | The project/programme outcome defines the changes in behaviour and circumstances experienced by the target population. This is the direct effect obtained at medium term resulting from the interventions and addressing the problems defined in the needs assessment.
Resultate | Output
Konkrete Leistungen (Produkte, Güter, Service) die im Projekt/Programm entstehen sowie deren Benutzung durch die Zielgruppe. Sie schaffen die notwendigen Voraussetzung um das Projekt/Programmziel zu erreichen. Es sollte daher eine klare Interventionslogik von Resultaten zu Projekt-/Programmziel geben. Projekte/Programme können mehrere Resultate auflisten, bitte entsprechend nummerieren. | Outputs describe the direct deliverables (goods and services) as well as their use by the target population, which are provided by the action that the project/programme is implementing, in order to achieve the aim defined at outcome level. Therefore, the logic of the chain from output to outcome needs to be clear. Projects/Programmes include more than one output. Please number them accordingly
Indikatoren | Indicators
Indikatoren sind qualitative und quantitative Werkzeuge zur Messung der Erreichungsgrads der Ziele und Resultate. Sie stellen eine Zustandsbeschreibung dar (was gemessen wird). Es sollte darauf geachtet werden, dass gewählte Indikatoren internationalen Standards (z.B.: SPHERE, Cluster) und der SMART-Regel entsprechen. Es können mehrere Indikatoren angegeben werden. Bitte entsprechend Zeilen hinzufügen oder löschen. | Indicators are qualitative and quantitative tools used to objectively measure the progress and achievement of the project/programme. These should be objectively verifiable, SMART and take existing standards into account (e.g. SPHERE, Cluster). As they are performance measures, they only define what is examined. It is possible to list a number of indicators. Please add or delete lines as necessary.
Meilensteine und Ziel | Milestones and target
Meilensteine sind fest gesetzte Zeitpunkte an denen ein Soll-Ist-Vergleich zwischen den gesetzten und erreichten Zielen gemacht wird, und somit Aussagen über dien Fortschritt des Projektes/Programms ermöglicht. Für jeden Indikator sollte ein Ausgangswert formuliert werden. Ziele sollten vor Projektbeginn festgelegt werden. Die konkreten Termine und Anzahl der Meilensteine müssen in Absprache zwischen den Zuwendungsempfängern und Sachbearbeitern beschlossen werden. | Milestones are used to indicate at specific, relevant junctures how the project/programme is progressing along the predicted trajectory. Therefore allowing for improved monitoring and enabling the implementation of corrective measures should they be necessary. There should be existing data for the indicators at baseline level to adequately assess the progress made. Targets must be determined at the beginning of the project. Milestones should be set at appropriate intervals agreed upon with the relevant assistant desk officers.
Quellen und Mittel der Nachprüfbarkeit | Sources and means of verification
Beschreibt die Datenquellen welche die nötigen Zahlen und Informationen zur Anwendung der Indikatoren liefern, sowie wann, von wem und wie häufig diese gesammelt werden. | Sources of information and methods used to collect and report on the indicators, including who is a gathering the data, where and in which frequency.
Annahmen und Risiken | Assumptions and risks
Beschreibt Rahmenbedingungen, Voraussetzungen oder externe Faktoren die nicht vom Zuwendungsempfänger beeinflussbar sind, sich aber auf den Verlauf des Projektes/Programms positiv oder negativ auswirken können und gleichzeitig eine entscheidende Bedingung zur Erfüllung der Interventionslogik darstellen. | Factors outside the project's management control that may positively or negatively impact the realisation of the project/programme but are nonetheless vital to the fulfillment of the logic of intervention
Aktivitäten (Activities)
Aktivitäten sind die Handlungsschritte und Maßnahmen die notwendig sind, um die geplanten Resultate zu erzielen. Die eingetragenen Resultate aus dem Logframe werden automatisch übernommen. Pro Resultat können mehrere Aktivitäten angegeben werden, bitte entsprechend Zeilen hinzufügen oder löschen. | Activities articulate the actions and measures necessary to produce the desired output. The outputs recorded in the logframe will automatically be transferred. Each output can require a number of activities, please add or delete lines as necessary.
Meilensteine | Milestones
Meilensteine ermöglichen eine kontinuierlichen Verfolgung des Programm/Projektfortschritts und somit eine angemessene Steuerung. Zeitpunkt und Häufigkeit der Meilensteine sind in Absprache zwischen Zuwendungsempfänger und Sachbearbeiter festzulegen. | Milestones enable the project management to track the progress of the activities towards the target, thus acting as an early warning system. The exact date and number of milestones should be agreed by donor and implementing partner together and ideally reflect the milestones used in the logframe.

## Logframe
Logframe Bitte Ausfüllhinweise beachten (Please consider the guidance notes)
Auswärtiges Amt - Referat S09
Antragsteller Applicant | Handicap International e. V. | [5 empty] | Datum Date | 2023-06-28
Projekt/Programm Project/Programme | Comprehensive Humanitarian Mine Action and Protection response to the crisis-affected population in Yemen | [5 empty] | Meilensteine (Daten) Milestones (Dates) | 1: 30/9/2023 2: 31/03/2024 3: 30/09/2024 4: 30/06/2025
Geschäftszeichen AA Reference Number GFFO | YEM/YEM/Handicap/2023/01
Antragsdatum Date of Application | 2023-06-28
Projektlaufzeit Project Duration | von from | 2023-07-01 | bis till | 2025-06-30
Oberziel Impact
Enhance functional independence, psychosocial well-being, safety and resilience of crisis-affected persons including people with functional limitations and EO victims through promoting access to integrated rehabilitation services, humanitarian mine action and disability inclusion
Projektziel/Programmziel Outcome 1
Improve the access for persons with disabilities, injuries and their caregivers to quality integrated health services including physical and functional rehabilitation care, MHPSS and provision of P&O services | Indikator 1 Indicator 1 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target | Annahmen und Risiken Assumptions and risks
| % of beneficiaries with functional limitations served by HI services that have shown improvement in their functional independence | Geplant Planned |  | 80% | 80% | 80% | 80% | 80% | 1. The security situation deteriorates substantially in intervention areas. 2. Access constraints can limit mobilizing teams in the targeted communities and can affect reaching targeted beneficiaries. 3. Delaying the authorizations and bureaucratic administrative procedure might not allow HI to access and intervene in the targeted areas on time 4. Strong commitment and approval requirements from local mine action authorities
|  | Erreicht Achieved |  | 0 | 90.78% | 84%
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
Beneficiary Pack, Beneficiary Database
| Indikator 2 Indicator 2 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| % of beneficiaries with functional limitations served by HI MHPSS services that have shown improvement in their psychosocial well-being | Geplant Planned |  | 80% | 80% | 80% | 80% | 80%
|  | Erreicht Achieved |  | 0 | 100% | 93%
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
Beneficiary Pack, Beneficiary Database
| Indikator 3 Indicator 3 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| % of caregivers who attended positive parenting skills sessions, that reported improvement in their knowledge and skills on positive parenting | Geplant Planned |  | 80% | 80% | 80% | 80% | 80%
|  | Erreicht Achieved |  | 0 | 0 | 100%
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
Pre-post assessments, Beneficiary Database
| Indikator 4 Indicator 4 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| % of the local health facilitates workforce that attended the capacity building training and reported improvement in their skills and knowledge. | Geplant Planned |  | 90% | 90% | 90% | 90% | 90%
|  | Erreicht Achieved |  | 0 | 0 | 98%
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
baseline and endline assesments, training reports
| Indikator 5 Indicator 5 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| % of community members that reported enhancement in their knowledge on psychosocial distress | Geplant Planned |  | 80% | 80% | 80% | 80% | 80%
|  | Erreicht Achieved |  | 0 | 80%% | 76%
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
Attendance sheet- Pre and Post tests
Resultat 1 Output 1
Persons with disabilities, injuries and their caregivers have access to quality integrated health services including physical and functional rehabilitation care, MHPSS, and provision of P&O services | Indikator 1 Indicator 1 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target | Annahmen und Risiken Assumptions and risks
| # of beneficiaries with functional limitations served by HI rehabilitation services including physical and functional rehabilitation, and /or ADs | Geplant Planned |  | 1312 | 2624 | 2625 | 3937 | 10498 | 1. The security situation deteriorates substantially in intervention areas. 2. Access constraints can limit mobilizing teams in the targeted communities and can affect reaching targeted beneficiaries. 3. Delaying the authorizations and bureaucratic administrative procedures might not allow HI to access and intervene in the targeted areas on time 4. Strong commitment and approval requirements from local mine action authorities
|  | Erreicht Achieved |  | 0 | 1154 | 2397
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
Beneficiary Pack, Beneficiary Database,
| Indikator 2 Indicator 2 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| # of beneficiaries with physical and functional limitations served by HI MHPSS services | Geplant Planned |  | 1312 | 2624 | 2625 | 3937 | 10498
|  | Erreicht Achieved |  | 0 | 39 | 1208
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
Beneficiary Pack, Beneficiary Database
| Indikator 3 Indicator 3 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| # of beneficiaries that received P&O device services | Geplant Planned |  | 34 | 102 | 102 | 162 | 400
|  | Erreicht Achieved |  | 0 | 10 | 54
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
Beneficiary Pack, Beneficiary Database, Donation certificated
| Indikator 4 Indicator 4 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| # of children with malnutrition that received stimulation therapy | Geplant Planned |  |  | 443 | 443 | 554 | 1440
|  | Erreicht Achieved |  | 0 | 0 | 99
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
Beneficiary Pack, Beneficiary Database
| Indikator 5 Indicator 5 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| # of parents/caregivers that received positive parenting skills sessions and need-based MHPSS service | Geplant Planned |  |  | 443 | 443 | 554 | 1440
|  | Erreicht Achieved |  | 0 | 0 | 99
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
Beneficiary Pack, Beneficiary Database,attendance sheet
| Indikator 6 Indicator 6 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| # of local health facilities workforce that received capacity building training | Geplant Planned |  | 16 | 49 | 49 | 73 | 187
|  | Erreicht Achieved |  | 0 | 0 | 48
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
Donation certificates- Training reports
| Indikator 7 Indicator 7 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| # of community members reached by awareness raising and psychoeducation sessions on psychosocial distress | Geplant Planned |  | 376 | 1127 | 1127 | 1690 | 4320
|  | Erreicht Achieved |  | 0 | 3568 | 4134
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
Attendance sheet, database
Projektziel/Programmziel Outcome 2
The communities living in and returning to highly contaminated areas feel safer from explosive ordnance hazards after receiving humanitarian mine action services by the end of the project | Indikator 1 Indicator 1 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target | Annahmen und Risiken Assumptions and risks
| % of surveyed individuals in affected communities reporting the adoption of safer behaviors towards EO | Geplant Planned |  |  |  | 80% | 80% | 80% | 1. The security situation deteriorates substantially in intervention areas. 2. Access constraints can limit mobilizing teams in the targeted communities and can affect reaching targeted beneficiaries. 3. Delaying the authorizations and bureaucratic administrative procedures might not allow HI to access and intervene in the targeted areas on time 4. Strong commitment and approval requirements from local mine action authorities
|  | Erreicht Achieved |  |  |  | 0 | 0
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
KAP surveys (baseline and endline)
Resultat 2 Output 2
Threats posed by explosive ordnance among the communities living in and returning to highly contaminated areas are reduced through humanitarian mine action activities | Indikator 1 Indicator 1 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target | Annahmen und Risiken Assumptions and risks
| # of direct beneficiaries of EORE sessions (disaggregated by Age & Gender) | Geplant Planned | 0 | 0 | 4800 | 3200 | 800 | 8800 | 1. The security situation deteriorates substantially in intervention areas. 2. Access constraints can limit mobilizing teams in the targeted communities and can affect reaching targeted beneficiaries. 3. Delaying the authorizations and bureaucratic administrative procedures might not allow HI to access and intervene in the targeted areas on time 4. Strong commitment and approval requirements from local mine action authorities
|  | Erreicht Achieved |  | 0 | 3836 | 3797
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
EORE activity reports, project database
| Indikator 2 Indicator 2 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| # of EORE Mass Media Campaigns implemented | Geplant Planned | 0 | 0 | 1 | 1 | 0 | 2
|  | Erreicht Achieved |  | 0 | 0 | 0
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
Photos, videos , recordings of the media campaign, report of the activity
| Indikator 3 Indicator 3 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| # of community focal points trained on EORE and Victim Assistance identification & referral | Geplant Planned | 0 | 0 | 11 | 12 | 17 | 40
|  | Erreicht Achieved |  | 0 | 0 | 0
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
Training Reports - Attendance sheets - Pre and Post tests - Certificates
| Indikator 4 Indicator 4 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| # of Non-Technical Surveys conducted to identify EO hazardous areas | Geplant Planned | 0 | 0 | 0 | 144 | 0 | 144
|  | Erreicht Achieved |  | 0 | 0 | 25
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
NTS reports
| Indikator 5 Indicator 5 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| # of personnel from NA trained or supported by capacity building activities (disaggregated by DGA) | Geplant Planned | 0 | 0 | 17 | 36 | 17 | 70
|  | Erreicht Achieved |  | 0 | 0 | 19
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
Training Reports- Attendance sheet- Pre and Post test
| Indikator 6 Indicator 6 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| # of EOD spot tasks conducted | Geplant Planned | 0 | 0 | 30 | 30 | 30 | 90
|  | Erreicht Achieved |  | 0 | 0 | 30
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
EOD Spot task IMSMA forms - EOD spot task IMSMA completion reports
| Indikator 7 Indicator 7 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| # of Community Safety Committee set up | Geplant Planned | 0 | 0 | 18 | 18 | 9 | 45
|  | Erreicht Achieved |  | 0 | 0 | 0
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
Meeting minutes, attendance sheets
| Indikator 8 Indicator 8 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| # of community safe areas established | Geplant Planned | 0 | 0 | 6 | 0 | 0 | 6
|  | Erreicht Achieved |  | 0 | 0 | 0
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
Completion reports
Projektziel/Programmziel Outcome 3
The access of the crisis-affected persons with disabilities and injuries to a range of protection, rights, and entitlement services in their communities has improved in collaboration with local CSOs, OPDs and key stakeholders | Indikator 1 Indicator 1 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target | Annahmen und Risiken Assumptions and risks
| % of local CSOs and OPDS participants who reported increase on their knowledge and skills on inclusion and the rights of persons with disabilities | Geplant Planned |  | 80% | 80% | 80% | 80% | 80% | 1. The security situation deteriorates substantially in intervention areas. 2. Access constraints can limit mobilizing teams in the targeted communities and can affect reaching targeted beneficiaries. 3. Delaying the authorizations and bureaucratic administrative procedure might not allow HI to access and intervene in the targeted areas on time 4. Strong commitment and approval requirements from local mine action authorities
|  | Erreicht Achieved |  | 0 | 0 | 94% | 0%
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
Training Reports- Attendance sheet- Pre and Post test
| Indikator 2 Indicator 2 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| % of stakeholders who reported increased awareness and recognition of the impact of Yemen crisis to persons with injuries and disabilities and their specific needs and rights | Geplant Planned |  | 80% | 80% | 80% | 80% | 80%
|  | Erreicht Achieved |  | 0 | 0 | 0 | 0
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
baseline and endline assesments, training reports
Resultat 3 Output 3
Crisis-affected persons with disabilities and injuries have access to a range of protection, rights, and entitlements services in their communities in collaboration with local CSOs, OPDs and key stakeholders | Indikator 1 Indicator 1 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target | Annahmen und Risiken Assumptions and risks
| # of crisis-affected persons with disabilities and injuries who received referral information and guidance. | Geplant Planned |  | 8 | 49 | 49 | 74 | 180 | 1. The security situation deteriorates substantially in intervention areas. 2. Access constraints can limit mobilizing teams in the targeted communities and can affect reaching targeted beneficiaries. 3. Delaying the authorizations and bureaucratic administrative procedure might not allow HI to access and intervene in the targeted areas on time 4. Strong commitment and approval requirements from local mine action authorities
|  | Erreicht Achieved |  | 0 | 0 | 159
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
Referral database
| Indikator 2 Indicator 2 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| # of local CSOs and OPDs participants who attended the seminars and sessionson the rights of persons with disabilities and inclusion | Geplant Planned |  | 0 | 7788 | 7788 | 3894 | 19470
|  | Erreicht Achieved |  | 0 | 6797 | 9418
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
Sessions, Seminars' Reports, attendance sheets
| Indikator 3 Indicator 3 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| # of advocacy meetings and events organized to promote the improvement of access to humanitarian services for crisis-affected persons with disabilities and injuries | Geplant Planned |  | 0 | 2 | 2 | 2 | 6
|  | Erreicht Achieved |  | 0 | 0 | 5
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
meetings and events' reports, attendance sheets
| Indikator 4 Indicator 4 |  | Ausgangswert Baseline | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| # of media and public outreach campaigns conducted to raise awareness of the rights, access, and entitlements of crisis-affected persons with disabilities and injuries conducted | Geplant Planned |  | 0 | 2 | 0 | 0 | 2
|  | Erreicht Achieved |  | 0 | 0 | 0
Quellen und Mittel der Nachprüfbarkeit Sources and means of verification
media campain materials (vedios, photos...etc), media reports

## Aktivitäten (Activities)
Aktivitäten (Bitte Ausfüllhinweise beachten) Activities (Please consider the guidance notes)
Auswärtiges Amt - Referat S09
Antragsteller Applicant | Handicap International e. V. |  |  |  | Datum Date | 2023-06-28
Projekt/Programm Project/Programme | Comprehensive Humanitarian Mine Action and Protection response to the crisis-affected population in Yemen |  |  |  | Meilensteine (Daten) Milestones (Dates) | 1: 30/9/2023 2: 31/03/2024 3: 30/09/2024 4: 30/06/2025
Geschäftszeichen AA Reference Number GFFO | YEM/YEM/Handicap/2023/01
Antragsdatum Date of Application | 2023-06-28
Projektlaufzeit Project Duration | von from | 2023-07-01 | bis till | 2025-06-30
Resultat 1 Output 1
Persons with disabilities, injuries and their caregivers have access to quality integrated health services including physical and functional rehabilitation care, MHPSS, and provision of P&O services | Aktivität 1.1 Activity 1.1 |  | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| Provision of integrated rehabilitation services (physical and functional rehabilitation, MHPSS, and donation of ADs) | Geplant Planned | 2590 | 5179 | 5180 | 7769 | 20718
|  | Erreicht Achieved | 0 | 2228 | 4495
| Aktivität 1.2 Activity 1.2 |  | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| Provision of Stimulation Therapy to children with malnutrition including orientation on positive parenting skills and need-based MHPSS service to the primary caregivers | Geplant Planned |  | 886 | 886 | 1108 | 2880
|  | Erreicht Achieved |  | 0 | 198
| Aktivität 1.3 Activity 1.3 |  | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| Strengthening of rehabilitation services in local health facilities | Geplant Planned | 16 | 49 | 49 | 73 | 187
|  | Erreicht Achieved | 0 | 0 | 48
| Aktivität 1.4 Activity 1.4 |  | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| Provision of awareness raising and psychoeducation sessions on psychosocial distress at community level and referral of people with mental health and psychosocial issues to need based available services | Geplant Planned | 376 | 1127 | 1127 | 1690 | 4320
|  | Erreicht Achieved | 0 | 3568 | 4134
| Aktivität 1.5 Activity 1.5 |  | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| Provide definitive P&O device services through selective service providing centers and/or through mobile workstation within the selected communities and IDP camps | Geplant Planned | 34 | 102 | 102 | 162 | 400
|  | Erreicht Achieved | 0 | 10 | 54
Resultat 2 Output 2
Threats posed by explosive ordnance among the communities living in and returning to highly contaminated areas are reduced through humanitarian mine action activities | Aktivität 2.1 Activity 2.1 |  | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| Conduct direct community awareness raising activities including mass media campaigns on the risks posed by explosive ordnance to promote safer behaviors among people affected by armed violence. | Geplant Planned | 0 | 4800 | 3200 | 800 | 8800
|  | Erreicht Achieved | 0 | 3836 | 3797
| Aktivität 2.2 Activity 2.2 |  | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| Identify, train and follow-up community focal points on basic EORE, Victim and Accident reporting and basic PSS, to identify beneficiaries in need of Victim Assistance services | Geplant Planned | 0 | 11 | 12 | 17 | 40
|  | Erreicht Achieved | 0 | 0 | 0
| Aktivität 2.3 Activity 2.3 |  | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| Refer victims and survivors affected through explosive ordnance to HI’s physical, functional rehabilitation and MHPSS services as well as external service provisions for emergency medical care and other humanitarian services | Geplant Planned | 0 | 118 | 78 | 0 | 196
|  | Erreicht Achieved | 0 | 0 | 36
| Aktivität 2.4 Activity 2.4 |  | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| Conduct Non-Technical Surveys (including NTS trainings) to identify suspected or confirmed hazardous area (SHA/CHA) in order to prioritize the lands to cancel, reduce or clear | Geplant Planned | 0 | 0 | 144 | 0 | 144
|  | Erreicht Achieved | 0 | 0 | 25
| Aktivität 2.5 Activity 2.5 |  | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| Assess, train and mentor national capacity through the creation of rapid response mobile Explosive Ordnance Disposal (EOD) teams capable of responding to Explosive Ordnance (EO) spot tasks in highly contaminated areas with the joint coordination with Mine Action Authority (MAA) | Geplant Planned | 0 | 17 | 36 | 17 | 70
|  | Erreicht Achieved | 0 | 0 | 19
| Aktivität 2.6 Activity 2.6 |  | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| Set up, train and support the Community Safety Committees – to increase community engagement, sustainability and resilience to cope up with the challenges posed by explosive ordnance and armed violence | Geplant Planned | 0 | 18 | 18 | 9 | 45
|  | Erreicht Achieved | 0 | 0 | 0
| Aktivität 2.7 Activity 2.7 |  | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| Establish safe areas in consultation with communities in cleared areas to mitigate the risks posed by explosive ordnance | Geplant Planned | 0 | 6 | 0 | 0 | 6
|  | Erreicht Achieved | 0 | 0 | 0
Resultat 3 Output 3
Crisis-affected persons with disabilities and injuries have access to a range of protection, rights, and entitlements services in their communities in collaboration with local CSOs, OPDs and key stakeholders | Aktivität 3.1 Activity 3.1 |  | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| Support existing referral system to ensure that crisis-affected persons with disabilities and injuries and their caregivers have access to a range of protection, rights, access, and entitlements services in their communities | Geplant Planned | 8 | 49 | 49 | 74 | 180
|  | Erreicht Achieved | 0 | 0 | 159
| Aktivität 3.2 Activity 3.2 |  | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| Conduct seminars and sessions to sensitize rights of persons with disabilities on inclusion to humanitarian actors, organizations of people with disabilities (OPDs) and communities’ and collaboration with Inclusion Task Force | Geplant Planned | 0 | 7788 | 7788 | 3894 | 19470
|  | Erreicht Achieved | 0 | 6797 | 9418
| Aktivität 3.3 Activity 3.3 |  | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| Advocate and coordinate with international, local actors and CSO/OPDs on the impact of Yemen crisis to persons with injuries and disabilities and on improving access to humanitarian services | Geplant Planned | 0 | 2 | 2 | 2 | 6
|  | Erreicht Achieved | 0 | 0 | 5
| Aktivität 3.4 Activity 3.4 |  | Meilenstein 1 Milestone 1 | Meilenstein 2 Milestone 2 | Meilenstein 3 Milestone 3 | Meilenstein 4 Milestone 4 | Ziel Target
| Engage in media and public outreach campaigns to raise awareness of the rights, access, and entitlements of crisis-affected persons with disabilities and injuries | Geplant Planned | 0 | 2 | 0 | 0 | 2
|  | Erreicht Achieved | 0 | 0 | 0